A PLAN FOR THE LAUNCHING OF THE YOUTH EMPLOYMENT 
SUMMIT (YES) NETWORK IN BURUNDI 

2002-2003 and Beyond

I. 
Introduction: 

According to the present rate and situation of the unemployment youth in Burundi, with the YES's objectives and plans for the future,  towards the youth, in involving  Youth Organizations, NGOs  and private sectors,  which have a desire to make their contributions  for the youth employment,  there is no doubt that YES will contribute in bringing hope,  through helping create more opportunities for the youth employment. This will give a future hope for the youth of Burundi and contribute more in peacebuilding, because peace starts within a person, from the person to the family, from the family to the society and from the society to the whole nation. This is only possible when someone can hope that he has the minimum of his/her living for tomorrow. 

II. 
Plan for the launching of YES:

June-September 2002

1.) Identifying, contacting and informing  the Representatives of different  Youth 

Organizations, NGOs, and different Sectors,  and share with them about YES 

2.) Build a Burundi delegation to the Youth Employment Summit. 

3.)Organize a small meeting of representatives from Youth Organizations, NGOs and Private Sectors interested by YES' program and share with them about YES  and the vision we have for the youth in Burundi

4.)Get information related to the youth unemployment and to the growth of the population of Burundi, and how to create opportunities as the solution to the issue

October 2002-January 2003  

1.) Sharing the outcomes of YES held in Alexandria,  Egypt  with the Youth Organizations,  NGOs, Private Sectors’ Representatives 

1.) Establish a  Steering committee 
2.) Organize a YES Consultation 

February-June 2003

1.) Organize a YES  in Burundi and,

2.)  Raise funds for the youth employment summit 

III.
Youth Employment Campaign

July-December 2003 and beyond

1.) Organize a Youth Employment Campaign

2.) Create job opportunities through  establishing scale projects

3.) Continue build a sustainable network with all sectors and to wide  the vision and Youth employment program  in Burundi

4.)  Continue to create more job opportunities and strategies to help make possible this work.

Prepared by:

Prosper Ndabishuriye

National Coordinator of YES in Burundi

