World Youth Forum Toward G8 Summit

-For Sustainable Society-

Title:
World Youth Forum Toward G8 Summit -For Sustainable Society-
(abbreviation: World Youth Forum/WYF)
Program Overview:
Date:

June 27th-30th 2008
Venue:
National Olympics Memorial Youth Center (Shibuya, Tokyo, Japan)
Participants:

Global Youth Leaders (80 youth from Japan, 80 youth from the other countries. )

Japanese Youth 

Organizer:

Japan Youth G8 Project (JYG8)

Co-organizer(Japanese youth organization and its networks):

A SEED JAPAN
Youth, Development and Peace Japan Network
Japan Youth Ecology League
Goal and Objectives:

1. Integrating the voice of youth from Japan and allover the world as a statement which is the suggestion toward G8 summit and youth’s own action plan, and announcing it to the society.
2. Constructing international youth’s network realizing the outcome of this conference.

Program:
	Date
	Time
	Period
	Content

	27(Fri)
	17:00
	60
	Opening Plenary

	
	18:00
	120
	Reception

	
	20:00
	120
	Poster session

	28(Sat)
	9:00
	20
	Morning Meeting

	
	9:30
	150
	Discussion about　Youth activity's role in the society

	
	12:00
	90
	Lunch

	
	13:30
	90
	Keynote Speech

	
	15:30
	150
	Section Meeting for issues

	
	18:20
	70
	Dinner

	
	19:30
	150
	Free session

	29(Sun)
	9:00
	20
	Morning Meeting

	
	9:20
	160
	Section Meeting for issues

	
	12:00
	60
	Lunch

	
	13:00
	120
	Session for implementation

	
	15:30
	150
	Action Planning

	　
	18:30
	90
	Dinner

	　
	20:00
	120
	Free session

	30(Mon)
	9:00
	20
	Morning Meeting

	
	9:20
	60
	approving the statement

	
	11:00
	60
	Closing

	
	13:00
	　
	Press conference

Appeal to the policy makers, embassies


Organization:
“Japan Youth G8 Project” is a youth project for “World Youth Forum” and side campaigns.
About 40 youth, most of them are university students, are the members of “Japan Youth G8 Project.”
Chair: Fukushima, Hiroki
President of World Youth Forum: Junya Tanaka

Sections are in below.

Section for General Affairs


Section for Program

Section for Foreign Participants

Section for Participants from Japan


Section for Finance and Logistics


Section for Public Relations


Side Campaign Team

Schedule:

Sep 2007
Launch of English web-site

Feb 2008
First announce in English for foreign youth leaders
April 1 2008
Application open

April 10 2008
Application first close
April 14 2008
Fixing the participants (of first close)

April 19 2008
Sending the documentation for visa

May 10 2008
Second close (mainly participants from countries needless to get visa for Japan.)
June 27th-30th 2008
Japan Youth Forum

July 7-9 2008
G8 Summit (in Toyako Lake area)

Budget:

Rete: $1=100 Japanese Yen
(1) Revenue
<Sum $150,000>

From Ford Foundation ($100,000)

Other Source of Founding

The Japan Foundation ($10,000)

Japan Fund for Global Environment ($20,000)
Private Companies (less than $10,000)
Fee from participants


Fee ($100 per person) of participants from Japan and other developed counties (($10,000))
(2) Expenditure

<Sum $150,000>

Subsidy to air tickets for participants from developed counties ($20,000)
Subsidy to air tickets for participants from developing counties ($60,000)
Accommodation, Dinner ($30,000)
Domestic Transportation, Correspondence, Printing, and Other Expenses ($20,000)

Personal cost ($10,000)

Reserve ($10,000)

Contact:

Ishikawa, Haruya (Vice President of World Youth Forum, Student of Keio University)


81-80-5242-2045 (Mobile Phone)

info@youthsummitjapan.com, haruya.ishikawa@gmail.com
Web-site


http://www.youthsummitjapan.com/
PAGE  
3

