PROSTAR Club
SMJK Katholik,

Jalan 10/3,

46000 Petaling Jaya,

Selangor Darul Ehsan.

Miss Margaret Lim,
Senior Assistant of Co-Curricular Activities,
SMJK Katholik,

Jalan 10/3,

46000 Petaling Jaya

Selangor Darul Ehsan.                                                                7 JANUARY 2011

Dear Ms Margaret,
A Request for Permission to organize HIV / AIDS Prevention Week (2011)
With reference to above, I, Yee Min Yan, as the secretary of this project, would like to request for permission of launching HIV / AIDS Week.

2. 
Our objectives of launching this project are to raise the awareness about HIV / AIDS among students and to equip students with sufficient knowledge about HIV / AIDS to protect themselves. 

3. 
Our HIV / AIDS Prevention Week will be held from 14 February till 18 February 2011. During this week, we would like to have:

-A HIV / AIDS information session with Form 4 students.
-A short quiz for students will be available at the booth

-A booth for selling our T-Shirt and an exhibition at the Anjung Kasih for the whole week.

4. 
I hope that you will consider it and approve our request. Thank you for your attention and cooperation. Thank you. 

Secretary,                                                                            Project Coordinator,

__________________                                                         ___________________

(YEE MIN YAN)                                                                   (NG HUI XIN)

Teacher Advisor,                                                                   Senior Assistant, 

___________________                                                       ___________________

(PN SHANBAGADEVI)




(MS. MARGARET)

Sekolah Menegah Jenis Kebangsaan Katholik

 Petaling Jaya

Proposal of 

HIV / AIDS Week Project

(2011)

From

PROSTAR Club

· 1.1 List of Project Committees
· 1.2 Schedule 
· 1.3 Budget
· 1.4 Activities
Objectives
· To provide students with sufficient knowledge about HIV/AIDS to protect themselves

· To raise awareness about HIV/AIDS among students

· To eliminate discrimination, fear and stigma towards people infected with HIV/AIDS by debunking myths about HIV/AIDS
1.1 List of Project Committees
Project Coordinator : Ng Hui Xin

Assistant of Project Coordinator : Tan Kah Yee 

Human Resource Coordinator : Leong Yin Mun

Secretary : Yee Min Yan

Finance Director : Peh Bo Fang
Public Relations Director : 

1) Dhaniah

2) Yong Lee Kwong
3) Tan Sze Teng

4) Ding Pei Ling
ICT Director : 1) Chan Si Ning
Logistics Coordinator : Fum Kar Yee
Research and Development Coordinator: 1) Tan Peck Yeng

                                                                   2) Tan Fang Yin
Artistic Team : 1) Ng Xin Yi

                        2) Yeo Jia Wen

                        3) Sum Shu Li
                        4) Chen Yee En

1.2 Schedule 
	Date
	Activity
	Timeline 

	14.2.2011
	Project Launching
	Assembly

	
	 HIV / AIDS Info Session for Form 4 Students

4S6, 4S7, 4S8, 4S9
	8.35 – 9.45am

 

	
	4P1, 4P2, 4P3, 4P4, 4P5
	10.40- 11.50am



	
	4S1, 4S2, 4S3, 4S4, 4S5
	11.50– 1.00pm


	14-18.2.2011
	Booth will be open 
	9.30am - 3pm 

	
	Exhibition at Anjung Kasih 
	Whole Week


1.3 Budget

Expenses

Prizes 



3 x RM10 = RM30

T Shirt 



120 x RM15 = RM1800 

Poster 



25 x RM 3.50 = RM 87.50
Red Ribbon Pins/Badges 

200 x RM 2 = RM 400

Revenue

T Shirt  (Price RM20)

120 x RM 5 = RM 600

Red Ribbon Pins/Badges

200 x RM 2 = RM 400

(Price RM4)

1.4 Activities

1.4.0. Project Launching
We will be giving short introduction about the project and invite Madam Lee to give a speech about issues on HIV/AIDS and youth. A board will be decorated used for this launching ceremony. 

1.4.1 HIV / AIDS Info Session

Students who went through the Peer to Peer Facilitation Training in November 2010 will present info on HIV / AIDS in 1 hour (2 periods). It will take 1 day to cover all Form 4 classes. AIESEC, an international organization with a chapter from University Malaya will join us in the info session. AIESEC’s students are exchange students from foreign countries and they also have undergone training by PT foundation on HIV / AIDS information. After the session, they can do a little of cultural sharing from their countries. It is hoped that this will attract attentions from students, and also assist us in session. 

1.4.2 Quiz 
A short 20 questions quiz will be available at the booth throughout the week for students to answer. Correct entries will be entitled for a draw and 3 prizes will be given out.

1.4.3 Booth and Exhibition
Remaining T-Shirts from Co-Curriculum Day and badges will be sold. A booth will be set up at the Foyer Block A for the whole HIV / AIDS Week from 14 February till 18 February 2011. 
Brochures supplied by Malaysian AIDS Council will be available for students to obtain.
Malaysian AIDS Council and AIESEC will supply the posters for exhibition. 

Also, as attached is a poster designed by the Artistic Team from our project committee. 

Prepared by,

Secretary,                                                                            Project Coordinator,

__________________                                                         ___________________

(YEE MIN YAN)                                                                   (NG HUI XIN)

Teacher Advisor,                                                                   Senior Assistant, 

___________________                                                         ___________________

(PN SHANBAGADEVI)




   (CIK MARGARET LIM) 

