YES Somalia Country Network

Project Title:



International Youth Development 

 IMPLEMENTATION PLAN  
 
Project Number:


IYD 

Estimate Starting Date:

Aug 2004

Completion Date:


12 Aug 2004

Implementing  Partners:

YES Somalia Country Network 

Executing Agency: 


UNICEF Somalia 

 

Total Budget:



US$ 4000 
Background
 Somali YES Country Network emerged with the result of Youth Employment Summit Held in Alexandria in September 2001 where world leader placed youth concerns on their top priorities by developing a frame work of action to support youth increasing youth populations in the world. Other outputs in this meeting which more than 80 world leaders and international organizations attended included establishment advocacy, information sharing and networking aimed to support youth groups.

 

In the establishment of Somali YES Country Network in 2002 by YES team delegates with the technical guidance of YES Secretariat in Boston moved forward into the implementation of Alexandria YES Summit plan of action by briefing youth groups and other potential stakeholders (CSO, International Organizations and Government representatives through a workshop held in June 2002. following wider collective commitment towards Youth empowerment, YES Somalia found institutional support (WAWA Network) through provision of office and communications facilities (internet), Steering Committee to support effective establishment of YES CN and undertake essential steps for extending and advocating, and designing YES CN plan of action were appointed. To receive wider support from other potential youth stakeholders YES Advisory Board consisting of influential people, local government and international organizations to support YES CN was appointed

Problem and Justification
World youth associations network had a ceremony of the world youth day in every year, in order to remember last event of world youths and what so far improved.

 The event is internationally recognized to express increasing challenge facing youths, ensure gaining wider support for youth through creation-enabled environment conductive for youth empowerment. Main theme of the event emphasized the need for development of youth sensitive policy and strategy by the government including incorporations of youth programmes responding youth concerns from the side of International Organizations involved in youth sector as well as the private sector.
Objectives:

1. To organize and bring together the youth groups local government, international NGO s professional persons, civil society religious and business community to alert to the global crises in youth development, vigorously put youth employment on the agenda, Education, health, awareness on HIV Aids , FGM, poverty ,peace promotion, demobilization of the militia, human rights and gender issue . 

2. To present youth concerns, options, and get broader support from Youth stakeholders to assist youth overcome such concerns through adoption of strategic frame work and policies responding youth concerns from government and, stakeholders

3. To present youth achievements and their role in social Development.

Activities
1. Selection of Organizing Committees of our member organizations in the three Sections of Somalia  (Hargeisa in Somaliland,  Garowe in Puntland , Mugdisho south Somalia ). These are the areas the international youth day event will be held. 

2. Inviting all the Participants 

3. Preparation of all the relevant materials (Slogans, stationeries, hand outs, facilitators, venue, Camera man and refreshments)

4. The events will be held within one day, the morning session we will have a workshop for seventy youth participants in every section and the afternoon session we would have open gathering that would be addressed by youth leaders, religious, business, governments, professionals and NGOs

5. Preparation of food /accommodations and transportation facilities.

6. Report writing.

Outputs

1. This day will be a rare intergenerational atmosphere of exchange and learning, it will be a tremendously exciting opportunity for senior leaders to meet the next generation of dynamic youth, the people who will lead our grandchildren in the future. 
2. Agree on the role of the youth in the new central government that is being finalized in Nairobi Kenya

3.  The participants (Youth) will learn the problems and effects of HIV/AIDS and FGM 

International Youth Day Work Plan 

	Sno
	Activities 
	Days 

	
	Description 
	6
	7
	8
	9
	10
	11
	12

	1
	Selection of Organizing Committees of our member organizations in the three Sections of Somalia  (Hargeisa in Somaliland,  Garowe in Puntland , Mugdisho south Somalia ). These are the areas the international youth day event will be held. 


	Xxxx
	Xxxx
	
	
	
	
	

	2
	Inviting all the Participants
	
	
	Xxxx
	
	
	
	

	3
	Preparation of all the relevant materials (Slogans, stationeries, hand outs, facilitators, venue, Camera man and refreshments
	
	
	
	Xxxx
	Xxxx
	Xxxx
	

	
	· The events will be held within one day, the morning session we will have a workshop for seventy youth participants in every section and the afternoon session we would have open gathering that would be addressed by youth leaders, religious, business, governments, professionals and NGOs

· Preparation of food /accommodations and transportation facilities.

· Report writing.


	
	
	
	
	
	
	Xxxx


