[image: image1.jpg]



Action Plan 

Western Europe Millenium Development Goal Campaign

Time period: February-July 2005

Wolfgang Gründinger, Regional Youth Editor, wolfgang@mdg.takingitglobal.org

AIMS:

· Build up an online network of at least 100 young activists involved in MDGs from all over Western Europe, thereof at least 50 from outside Germany

· Build-up of a databank of altogether at least 20 articles from young editors from all other Western Europe

· Accomplishment of an Open Youth Forum in a large city, dealing with MDGs

· Plan concrete steps for a Second and, if already possible, Third Open Youth Forum in another large city (outside Germany)

· Build-up of a takingITglobal MDG website and implementing links to this website in about 50 relevant websites of Western European NGOs and INGYOs in particular

· Publish at least 5 articles in various magazines; promoting the campaign in the media as far as possible

· Solicit and connecting existing initiatives

· Initiate activities and projects implemented by other organizations

· Lobby Western Europe Governments (Italy, Germany, France, Spain, Austria) 

· Attend relevant conferences, preferably as a contributor

· At least 5 talks in schools

· Several online chats

TIMELINE:

February:

· Contact relevant people and organizations

· Write first article

· Call for articles; build up a team of regional youth writers

· First links to website

· Extra regional website? Regional email newsletter? 

· Collect events

· Write governments and NGOs: what do they do?

· Contact local and other media for reports about the MDG campaign

Ongoing (in general):

· Solicit articles

· Collect events

· Email newsletter? Homepage actual?

· Solicit links to website

· Assist in creating monthly theme 

· Build-up further on team of regional youth writers

· Attend conferences / events

· Talks in schools etc.

March:

· Build-up regional website, regional newsletter ?

· Start organizing 1st Open Forum

· Ask for publishing an article is possible in different magazins

· Order business cards

· Solicit articles (at least 4)

· ongoing jobs

April:

· Set up regional discussion boards on TIG website, moderate them (1st of April)

· Promote Global Gallery, write contest

· Solicit articles (at least 4)

· ongoing jobs

May:

· Participate live chat

· Further steps toward 1st Open Forum

· Steps for 2nd Open Forum

· ongoing jobs

June:

· 1st Open Forum takes place

· steps to 2nd Open Forum

· ongoing jobs

· more (TIG tasks)

July:

· maybe 2nd Open Forum, or at least concrete steps

· ongoing jobs

· more (TIG tasks)

RELEVANT URLs & NGOs:

· YOIS Europe, http://www.yois-europe.org and national YOIS groups

· Global Contract Foundation, http://www.globalcontract.de

· Global Marshall Plan Initiative, http://www.globalmarshallplan.org

· Youth Action For Change, http://www.youthactionforchange.org

· International Youth Parliament Network, http://www.iyp.oxfam.org

· AIESEC (European and local)

· AEGEE (European and local)

· European Young Socialists, http://www.ecosy.org

· Deutscher Bundesjugendring, http://www.dbjr.de 

· EU Youth Forum, www.youthforum.org

· Youth Forum Baltic Sea, http://www.ljrsh.de and http://www.balticsea-youth.org

· Foundation for the Rights of Future Generations, http://www.srzg.de

· JEF Europe, http://www.jef-europe.net

· Roract, http://www.rotaract.org

· Proday, http://www.proday.org

· Servicestelle Jugendbeteiligung, http://www.jugendbeteiligung.org

· Friends of the Earth / BUNDjugend, http://www.foeeurope.org / http://www.bundjugend.de

· Youth Employment Summit, http://www.yesweb.org

· TakingITglobal

· KLJB, http://www.kljb.de

· SD Forum Passau, http://www.sdforum.de

· Attac, http://www.attac.de

· www.zeitdenken.de (redaktion@zeitdenken.de)

· www.jugendpresse.de (buero@jugendpresse.de)

· www.milleniumcampaign.org

· www.training-youth.net

· www.youthencounter.org

· YOIS contacts for Malta (policy test)

Contact furthermore:

· EU

· Auswärtiges Amt

· BMFSFJ

· BMZ

· governments in Italy, Spain, France

POSSIBLE TEAM PARTNERS :

· Karsten Wenzlaff

· Michel Vette

· Jenny Scheffler

· Renaud Pascal

· People from SD Forum / GMP

· Maike Sippel

· Simone Burger

· Antje Trosien

· IYP action partners

· TIG activists

Important: people from outside Germany!

