[image: image1.png]



National Information Society Youth Campaign

in Ukraine 2005
Creating a Plan 

(September 1, 2005 – October 25, 2005)
Implementing organization in Ukraine 

Title: “Information Society of Ukraine” Foundation www.isu.org.ua 
President: Andriy Kolodyuk
Coordinator: Inna Volkova, Program Director, “Information Society of Ukraine” Foundation
Postal address: 6 Patorzhynskogo str.
Kyiv, 01034, Ukraine
tel/fax: +380 44 502 0050
cell: +380 50 357 5370
Email: iv@isu.org.ua 
Campaign coordinator: Denis Stepura 

Email: dstepura@ukr.net 
Activities and Timelines

	August 15-31
	· Active promotion of National Essay Contest, “The Role of Youth in the Development of the Information Society in Ukraine” through youth organizations, schools, institutes, universities, internet portals, and youth media groups in Ukraine.



	September 1 – October 15
	· National Essay Contest, “The Role of Youth in the Development of the Information Society in Ukraine”.
· Ongoing active promotion through youth organizations, schools, institutes, universities, internet portals, and youth media groups in Ukraine.


	September 1-23
	· Preparation for the Open Forums (2 Forums) on youth and ICTs (identifying venues, identifying speakers, promoting Forums locally, developing thematic framework and relevant materials in Ukrainian).


	September 24

	· The first Open Youth Forum on ICTs (Kyiv City):
Place: conference hall City.Com
Audience: 100 persons
Type: Event
Speakers: 3 persons

Time: 5 hours
· Media-support (publications in the central media)



	October 8
	· The second Open Youth Forum on ICTs (Nikolaev City):

Place: conference hall of the Collage of Journalism
Audience: 80 persons

Type: Event

Speakers: 3 persons

Time: 5 hours

· Media-support (publications in the local media, TV program)



	October 15

	· Winners of the essay contest announced


	October 15-25
	· Preparation of the National Declaration summarizing the perspectives of Ukrainian youth (based on essays and reports from the Open Forums).
· The final report on the campaign in Ukraine is prepared for the Summit in Tunis.




Partners in Ukraine
FRI (Foundation of the regional initiatives)
· Enlist auditory (the main auditory will be the leaders of different youth NGO’s, and winners of different competitions connected with IT).
· Make e-mail marketing through the address list.
Independent Media Center 

· Organizational support.

· Media-support through the NET. 
Microsoft


· Active participating in the Forums as speakers.
· Present to the auditory information materials.
DA.NET (Internet Agency)  

· Active participating in the Forums as speakers.
· Advert and support of our project through the NET.
City.Com (Trading network of IT-hypermarkets, and e-shop of IT products) 

· Put in our disposal conference hall for (100 participant),  with all media equipment, with a rebate 70% 
Foundation “Ukrainian educational center of reforms” 

· Media-support of the project (articles in the central newspapers, a program on the one of TV channel)
PAGE  
1

