July 24th 2006 – Youth Organizing Committee
2 weeks and 6 days to go
	Action
	Person Responsible 
	Deadline
	Outcome

	Clothing – polo shirt, sweat bands, sporty jacket
	Erin to get in touch with contact
	This week
	We will have samples and prices to review on Monday – we’ll take orders then.

	Rough Global Village Booth 
	Staff will provide materials, YOC will provide materials and begin design
	next meeting
	

	Homestay Alternatives – Book Marko 
	Mike to look into U of T residence, Lisa to look into hostel availability, Kristy continuing with homestay
	Next meeting
	

	Fundraising
	Rohit – letter campaign through work – fantastic
YOC – ongoing

Mike – Picadily Circus

Stephen – Ball game

YCI – Letter Writing and online donations
	ongoing
	

	Speaking Tour 
	YOC, 
Laura, Mike – speaking tour coordinators
	This Saturday for additions to the list
Ryan has a deadline of this Saturday to communicate with partners re: their specific interests
	

	Dynamic Global Village
	Art Piece: Julie and Denis
Multi media: Shawn

Film: Denis


	Erin to get updates on all pieces for next Monday
	

	Training for the Global Village Volunteers
	Erin
	To be held one evening the week before the conference
	

	International Youth Day – Launch and Thank You
	Erin
	Event to be held on Aug. 12th
	

	
	
	
	


